Transition Milestones

The following example of transition milestones were developed to measure the successful implementation of the Transition of the PR to national entities. Good progress needs to be made towards achieving these milestones before grants can fully transition.

| Transition Milestones |  |
| --- | --- |
| 1 | The complete MOH PMU needs to be in place, with clear connecting lines of communication, accountability and feedback to and from the implementing directorates. |
| 2 | Capacity at the sub-national level is known and recommendations or capacity development plan for the sub-national is in place. |
| 3 | All operations and implementation manuals in place, based on national and Global Fund requirements and capacities required by PRs, endorsed by the MOH and 100% of staff trained. |
| 4 | Joint programme planning and review meetings taken place every quarter with discussions held on managing all risks. |
| 5 | Joint PU-DR development of the transitioning grants taken place for one year. |
| 6 | Final implementation arrangements for HIV Prevention activities agreed and set up to ensure continuation of activities. |
| 7 | Strengthened management competencies, to enable strong grant management and active oversight. |
| 8 | Capacity for forecasting and quantification is strengthened and institutionalized through the National Technical Working Group on quantification and procurement planning. |
| 9 | National Supply Chain has 100% of the required systems and staff in place to act as the lead on procurement and storage for the MOH. |
| 10 | Good Distribution Practices (GDP) systems, guidelines are in place, being utilized, with adequate supervision by trained staff at the national and at the peripheral level (including all districts and facilities) and in compliance with the relevant SOPs, resulting in a significant decrease in the numbers of stock outs and/or overstocks. |
| 11 | Logistic Management Information System data is reliable from national level up to the last mile and can be used to inform distribution plans and quantification at central level. |
| 12 | Financial systems are in place to support full programme implementation, with strong measurable controls and tracking tools; with the ability to generate accurate financial information, and able to support the increase in funds and transactions. |
| 13 | 100% of assets are documented and annual asset verification processes are in place. |
| 14 | The national HMIS and DHIS2 system is fully configured for the TB, HIV and Malaria grants being transitioned and has produced accurate programmatic data for one year. |
| 15 | All MOH staff within the PMU, and other implementing directorates have the required M&E skills to support the implementation, analysis and reporting on the GF grants. |
| 16 | All costed disease National Strategic Plans, with supporting M&E Plans are in place to support the next funding application in 2020. |
| 17 | Joint transition planning and review meetings taken place every quarter reviewing progress and managing all transition risks. |